## Sheet1
INFO6090 Weekly Team Meeting Progress and Planning Sheet
Team: | G08 |  | Member ID | Members(given, Family Name) |  |  |  |  | Members Present (ID)
|  |  | 1 | A |  |  |  |  | 1
Semester Week: |  |  | 2 | B |  |  |  |  | 2
|  |  | 3 | C |  |  |  |  | 3
|  |  | 4 | D |  |  |  |  | 4
Task ID (keep old ID's) | Task Description |  | Members Assigned (IDs) | Estimated Completion Date | Work In Progress (WIP) Due Date(s) | Work in Progress Uploaded Status | Task Status | Comments
W4-01 | Data Integration System |  | 1 | 2022-11-01 | 2022-11-02 | Done | Completed
W4-02 | Sql Tables and Schema |  | 2 | 2022-11-02 | 2022-11-03 | Done | Completed
W4-03 | Sales Forecasting Model |  | 4 | 2022-11-01 | 2022-11-03 | Done | Completed
W4-04 | Operational Efficiency Analysis |  | 3 | 2022-11-05 | 2022-11-05 | Done | Completed
W6-01 | Business Recommendations |  | 1 | 2022-11-06 | 2022-11-09 | Done | Completed
W6-02 | Advanced Analytics Dashboard |  | 2 | 2022-11-07 | 2022-11-11 | Done | Completed
W6-03 | Executive Summary |  | 4 | 2022-11-10 | 2022-11-12 | Done | Completed
W6-04 | Recorded Presentation |  | 3 | 2022-11-10 | 2022-11-11 | Done | Completed
W7-03 | Final Review |  | 2 | 2022-11-11 | 2022-11-11 | Done | Completed
W7-04 | Final Submission to Canvas |  | 2 | 2022-11-11 | 2022-11-11 | Done | Completed
Legend
Task ID: |  | Each task is to have a unique ID (the ID is repeated weekly until the task is reviewed, accepted and markeked as completed)
WIP Uploaded Status: |  | Yes, No
Task Status: |  | Completed, In Porgress, in Review, Reassigned to (member IDs)

## Week 4 Meeting
Week 4 Meeting | 1st Nov, 6-6:30 PM
Attendees | A, B, C, D
Minutes | Discussion of Assignment Requirements - Major Concepts: Find insights and recommendations - Data: Sales - Business Problems: 1. Identify top sales performers for incentives 2. Different approaches to reach the conclusion 3. Transfering data from excel to SQL, data cleansing. - working on Data Modeling
Task Allocation | 1. Problem Statment (20%) - C 2. Analysis (35%) - A 3. Data Model (10%) - D 4. Transfering data into Database - B
Next Action Items | 1. See the data & its trends to help in fidning insights. 2. Attend the weekly meeting 3. C to do some data processing, data cleansing, and high level data checks 4. Base Analysis: D,B to do some test logic for identifying top sale performers, least selling and top selling products

## Week 6 Meeting
Week 6 Meeting | 3rd Nov, 7-7:45 PM
Attendees | A, B, C, D
Minutes | 1. Discussion of SQL script and Schema 2. Further discussion about the assignment instructions/guidelines (analysis) 3. Writing the exectuive summary 4. Start preparing slides and video recording
Task Allocation | 1. Base Analysis, Business insights, Data processing - A 2. Presentation Slides, help A in finding insights - B 3. Executive summary & documentation work - C 4. Recorded video - D
Next Action Items | Next Meeting: Nov 04, Tuesday, 7-7:30 PM 1. A - Finalize SQL Schema (4th Nov morning), Video (Nov-10) 2. C Documentation & Other Materials (Nov 09 morning). 3. C Exec Summary (Nov 06 morning). 4. B PowerBi dshbord smple prep (Nov 06 Thursday ) 5. D Pre-recorded presentation - submit to A by Oct-07.

## Week 7 Meeting
Week 7 Meeting | 4th Nov, 7-8 PM
Attendees | John Wilson Mendoza Jon Voorby Priyanka Rajendra Savani Jasvinder Singh
Minutes | 1. Discussion of schema tables, SQL, Business insights and Logics. 2. Finalisation of Data Processing & ETL as well as , Analysis Report - Exec Summary, Introduction/Overview: C - Data Model: Schema+Data Process : A - Analysis: B - Recommendation: D
Task Allocation | 1. SQL Data Cleansing- A, D help in presentaion recording 2. SQL Data Cleansing, Data Checks, Base Analysis, Business Recommendations, Documentation (Admin + Final Paper) - B, C to help in documents 3. Executive Sumary, Data Processing - A , C (help in executive summary)
Next Action Items | A, B will create the Dashboard in PowerBi, A,D give final review of SQL Data Cleaning Process, C prepare the full report, A help C in executive summary